## Slide 1: Migration of SaaS Flex to MAS MS
Steps and Flows
V0.1

## Slide 2: Agenda
Key Findings
Review flow diagram
Review sizing mechanism for migration of clients
Summary of existing clients
Review labor estimates
Next Steps

## Slide 3: Key Findings
The move from SaaS Flex (or even on premise) to MAS MS is not just an upgrade – it is a migration of a customer’s application and data to a new data center account and / or new technologies
Clients will need to properly plan and account for this transition as part of their planning process.
Small customer will take 2-4 months elapsed time, medium 3-6, Large 5-12 and Extra large more than 10 months (up to 18). These are guidelines only.
To ensure a smooth transition, it is critical that IBM (Sales, CSM, MAS MS) and the client work together early to identify the steps needed and build the correct plan.

## Slide 4
Roles and Responsibilities
not covered within SaaS Flex contract

## Slide 5: SaaS Flex to MAS MS Migration – Overall steps
Planning
Precondition
Initial Set up
Test one
Test two
Production
Project Planning
Budget
Approvals
Timeframes
requirements definition
Quotes and any additional contracts required
Upgrade if needed
Deploy MAS MS and applications
Remediate changes as required
Setup integrations including any VPN
Upgrade to 8.3
Migrate database
Finish remediation of changes needed
Repeat the process of upgrading and migrating database
Test as required
Take accurate timings of steps for Production cutover
Cutover production weeked
Small: 2-4 months elapsed IBM 100 hours effort Client: 3-5 person month effort
Medium: 3-6 months elapsed IBM 240 hour effort Client: 4-8 person month effort
Large: 5-12 months elapsed IBM 500 hours effort Client: 10-18 person month effort
Planning and precondition are not included in the effort estimates. These are guidelines only
Extra Large: high complexity IBM 800 hours effort Client: 18+ person month

## Slide 6: SaaS Flex to MAS MS Migration – Planning Steps
Project Planning
Owner: Client
Assist: Sales, CSM, MAS MS
Includes:
  Budget
  Approvals
  Timeframes
  requirements definition
  Quotes and any additional contracts required
Project Initiation:
All contracts signed and order placed
Order validated through Project Office
Project Manager assigned
Formal Project plan completed
Personnel assigned
Approved
Further planning?
End
Pre Condition Phase

## Slide 7: SaaS Flex to MAS MS Migration – Initial Set up
Confirm order details, URL’s
Deploy MAS MS infrastructure and applications
Configuration of VPN if needed
- 1 week of effort but may take several weeks / months to complete depending on client approvals and process
Pre Condition Phase
Prepare test environment on SaaS Flex including – backflow data
Identify all components to be migrated (custom code, custom reports, attachments)
Configure integrations in new MAS
Remediate technical updates required
Assemble all identified components to be sent to MAS for test one.
Test One

## Slide 8: SaaS Flex to MAS MS Migration – Test One
Run upgrade to 8.x
Export database
Send to MAS MS Environment
  Time depends on size of DB being transferred
Send attachments, custom reports and other custom code to MAS MS environment
Initial Set up
Import database into MAS MS
Deploy custom files
Remediate technical differences
Some done by client / implementor
Some done by IBM MAS MS
Start Application and make it available to customer
Test application in new MAS MS environment
Report, trouble shoot and resolve issues
Test Two

## Slide 9: SaaS Flex to MAS MS Migration – Test Two
Run upgrade to 8.x
Export database
Send to MAS MS Environment
  Time depends on size of DB being transferred
Take careful timings for planning of production cutober
Send any delta’s of attachments, custom reports and other custom code to MAS MS environment
- There should be only a small set of attachments
Test One
Import database into MAS MS
Deploy custom files
Remediate technical differences
Some done by client / implementor
Some done by IBM MAS MS
Start Application and make it available to customer
Take careful timings for planning
Test application in new MAS MS environment
Report, trouble shoot and resolve issues
Production

## Slide 10: SaaS Flex to MAS MS Migration – Production
Run upgrade to 8.x
Export database
Send to MAS MS Environment
  Timing from test two
Send final delta’s of attachments, custom reports and other custom code to MAS MS environment
- There should be only a small set of attachments
Test Two
Import database into MAS MS
Deploy custom files
Remediate technical differences
Some done by client / implementor
Some done by IBM MAS MS
Start Application and make it available to customer
Timing from test two
Test application in new MAS MS environment
Report, trouble shoot and resolve issues
Client – checks to ensure things operational
IBM – as required
Complete