## Swimlane
| 1 - 6 months | 3 - 6 months | 1 week | Variable | 1 month | 1-4 months | 1 week | 1 - 2 months | Weekend
| Planning | Pre-conditions | Initial Set up |  | Test one |  | Test Two |  | Production cutover
|  | - upgrade only required if client is < than the minimum - currently 7.6.1.2 |  |  |  | Dependant on customer test requirements
Client | Project initiation - client process to allocate resources, project planning and internal approvals | Upgrade to 7.6.1.2 - testing | - begin VPN config as soon as MAS MS environments known - client network team | - Configure VPN |  | - Test the MAS MS instance |  | - Test the MAS MS instance | - Acceptance test
Client (Items that could be delegated to Lab Services, BP or GBS |  | Upgrade to 7.6.1.2 - config changes, remediation required | Itemize all componets that need to be migrated (attachments, JAVA files, customer reports |  | - after MAS MS environment up, remediate any items that be done through the Maxadmin user - make integration changes as needed - ensure SSO is working | - remediate any changes needed through Maxadmin user |  | - remediate any changes needed through Maxadmin user
IBM CDS (SaaS Flex) |  | Perform technical upgrade | backflow prod database to test environment to be used for test runs |  | - upgrade test DB to 8.5 (or current) ' export DB and ready for transfer along with identified attachments, JAVA Code and reports |  | - upgrade test DB to 8.5 (or current) ' export DB and ready for transfer along with identified attachments, JAVA Code and reports |  | - upgrade test DB to 8.5 (or current) ' export DB and ready for transfer along with identified attachments, JAVA Code and reports
IBM CDS (MAS MS) | Presales team support client planning and estimating |  | - Provision MAS MS environments - Provision Optimizer H/W if required - Install configure optimizer - Begin configration of VPN if required as soon as MAS MS Environment known | - Configure VPN (Network) |  | - Support testing of MAS MS instance (CC, other chapters as required) - remediate data issues, web application server issues, readhat issues (As required) | - receive DB and import to MAS MS testing area - start application -make config changes that only MAS MS can do with regard to the remediation items | - Support testing of MAS MS instance - remediate data issues, web application server issues, readhat issues | - receive DB and import to MAS MS testing area - start application -make config changes that only MAS MS can do with regard to the remediation items - support final acceptance testing

## Task description
Activity | Description
Prepare for project | This activity emcompasses the client process to plan, budget and approve a project. This can be short or a lengthy activity. If the client is in a regulated industry, this can add additional time for the planning and approval process. IBM supports this process with the Sales team, CSM, OM and the MAS MS Presales support team. The client will likely want to engage a 3rd party implementor to support them in this upgrade. This can be Lab Services, GBS or one of the Maximo Business Partners of the customer choosing.
Pre Conditions | This primarily involves ensuring the existing SaaS environment is ready. An upgrade may be required if client is less than 7.6.1.0. The client also needs to ensure all attachments are identified, JAVA class files known and any report files identified.
Initial Set up | This involves several activities which can occur in parallel. The initial install of the target MAS MS environment is done along with any other add-ons required including optimizer. As soon as the MAS MS envirionment is known then IBM and the client can begin working on the VPN if needed. The test environment to be used on the Saas Flex side is identified and a copy of production backflowed to it in preperation of the move.
VPN | This is a combination of IBM Network and client network personnel. For some clients, this can involve a lengthy internal approval process even when the SaaS Flex already exists. Clients need to ensure this approval is ready as soon as the final IP's are known for quick turnaround. The extreme example is a client who lost 4 months getting approvals through their network and security team.
SSO Set up | SSO needs to be identified and all the steps for both IBM and the client understood. Once the environment is ready and the VPN ready, the steps to make this available need to be executed. The process for SSO is different in MAS MS as it is done not at the Maximo level, but the MAS level.
Integration Set up | The client usually has the bulk of the configuration work on their internal systems and through the MAXADMIN user. IBM needs to be ready to assist with network issues and ensuring any web application server changes are done as required.
Remediation | The below are the identified differences from a technology perspective that need to be done as part of the migration. Some can be done ahead of time (SOAP 1.1 - 1.2 for example) and others need to be done after the database is migrated (Kafka instead of JMS). We need to understand the exact steps that need to be done and who can execute them.
SOAP 1.1
apikeys
Kafka (instead of JMS)
REST API (insteaad of RMI)
1st trial | CDS will run the upgrade script on the existing SaaS Flex (test) DB, and then export it. MAS MS will pull the DB and import it into the MAS MS database. Changes at this time need to be made for remediation as above, ensire SSO Works, placement of the appropriate JAVA code and attachments, building the EAR and starting the application. Teh client then needs to test to ensure all business processes and integrations work as expected. This can take weeks to months depending on the amount of testing required, the availability of personnel and the issues found.
2nd trial | A repeat of the first trial, except attachments, java code and reports do not need to be moved and integrations should be working. A fresh export is taken and transferred and loaded. Testing should ensure all previous issues are resolved. Timings are taken to understand the steps and check points for the cutover weekend.
Cutover | A final move with acceptance testing by the client for go live. The 2nd trial will determine how much time is neede dfor this.